## T Shirt Sizes
Container | T-Shirt Size | Notes
Priority Pass App
PP Mobile App (Additions) | M | A new card with a deep link should be quick. And parsing a new referal code when getting traffic from Taxi app also shouldn't require much work besides passing the data for the back end to process.
Priority Pass Back End Services
Registration Service | S | Service should already exist but may need to be updated to account for our new affilate (Taxi app) sending us leads and properly attributing them for it.
Attribution and Affiliate Service | L | Critical system, tracks attribution for correct billing
Consent and Privacy Service | M | Despite the lofty name the service and ledger are fairly simple to build
Journey Context Service | XL | API to provide flight/iterary data for a user. Requires extranl integrations which can take longer than anticipted.
Partner Orchstartion Service | XL | The parnter orchestration service is going to be the core engine behind this system to coordinating with external parters. Taxi app and possibly later airline apps or banking apps. Building in extra time to ensure the connection with Taxi apps get set up and throughly tested. See the component diamgram for an inside look.
Notificaiton Orchestrator | M | Existing notification infrastucture can be utilized and new events triggers set up.
Feature Flags and Rules | S | Lightweight config options can be build in or ideally leaverage an existing flagging framework.
Analytics and Event Tracking | M | Start simple track clicks and leads
Key Management and JWKS | M-XL | Depending on what existing intrfrastucture can be leavered and possible security review (road block) from PP and or Taxi app comany
Benefit Content API | S | Should already exist with possible minior tweaks needed to expect new external traffic
Priority Pass Data Layer
Member Profiles | N/A | Should already exist
Trip and Flight Context | M | Getting this initial data is easy but tracking state and updates adds a bit of complexity
Consent Ledger | S | Although important a ledger can be as simple as a single SQL table (plus a log table)
Event and Attribution Logs | M | Will be high volume, needs analytics, must be auditable
Caches and Queues | S | Ideally a cache is already infromt of the Journey context service if not applying one is quick. Message busses/Kafka is easy to utilize even if not already available.
External Provider (Integration)
Flight Data APIs | S | Assuming this is readily available and can be leaveraged from existing internal work
Maps and Traffic | L | Getting estimated travel times to the correct airport from the users location is easy with the Google Maps API. However, setting up a company account might require approval causing my higher estimate.
APNS and FCM | S | Assuming push notification intfrstructure is already set up for the Priority Pass app
App and Play Store | N/A | Freebie from phone OS
Global Taxi Parter |  | Not done by us but good to consider how long it might take our partner to do this work
Taxi Mobile App | L | Certainly a larger lift than the changes planned to the Priority Pass app. Require more API integration and an overall larger UI display and much more logic to consider
Taxi Partner Gateway | XL | Lumping all of their remaining backend changes here
Booking and Dispatch System | L | Will need to be updated to credit PP with a laed resulting in a booking